## Sheet1
Task and Describtion | 11/27-01/08 | 01/08-01/29 | 01/29-02/12 | 02/12-02/26 | 02/26-03/11 | 03/11-03/18 | 03/18-04/08 | 04/08-04/22
1. Discover how to get voltage readings from TDWLB0050034 device without using transducers direct smartphone application | Task 1
2. Create our own Android application through Android Studio that can connect to the TDWLB005034 device via Bluetooth, collect the voltage data from the device, and display that data onto the application screen. | Task 2
3. Test the BMA400 accelerometer component independently from the sensor to discover how to properly wire and ensure the group knows how it is supposed to work. | Task 3
4. Find a location within the Brain Ballast Sensor that can fit the BMA400 and allow it to work properly. | task 4
5. Install the BMA400 into the Brain Ballast Sensor |  | task 5
6. Test the device to ensure the BMA400 still works as intended within the Brain Ballast Sensor housing. |  | task 6
7. Connect the BMA400 device to our own application, send the data from the BMA400 through the same Bluetooth connection that the TDWLB0050034 device currently uses, and display that data on our Android application. |  |  | task 7
8. Using computer aided design (CAD) software tools to design a new housing for the Brain Ballast Sensor. |  |  |  | task 8
9. Research the different ways that we can manufacture the new housing for the device, whether it be from machine milling utilizing CNC or through one of Dr. Barry’s 3-D printers. |  |  |  | task 9
10. Using the machinery within BELL and assistance from one of our sponsors, Mr. Davis, create the new housing. |  |  |  |  | task 10
11. Buildout the Brain Ballast Sensor with current hardware. | [5 empty] | task 11
12. Test the new housing of the device with the ‘LS-DSS’ machine provided within our sponsor’s laboratory. | [5 empty] | task 12
13. Split the group into two groups where one will focus on extending the battery life of the device and the other will focus on improving the wireless connection of the device. | [6 empty] | task 13
14. If any discoveries are made implement them into the device | [6 empty] | task 14